## Sheet1
№ | Description | Responsible | Prerequisites | Done criteria | Status | Time
1 | Install Sap NetWeaver, connected it to SAP Cloud Platform | Shamil | No | 1. each team member connected to backend | Done | 1 day
2 | Implement back-end logic, create ODATA service | Shamil | Task 1 is finished | 1. ODATA is working 2. present to a team | Done | 7 days
3 | Lo-fi muckups | Shamil | No | 1. Show it to professor | Done | 1 hour
4 | Hi-fi muckups in ppt format | Marcia | Task 3 is finished | 1. team review 2. hi-fi mockup uploaded in github in editable format in design folder 3. Each screen uploaded in document folder as jpg 3. present to a team | Done
5 | Create prototype in build.me | Marcia | Task 4 is finished | 1. team review 2. present to a team | Done
6 | Ctreate personas, journeys (enduser, support team member, support team manager) | Ilkay | No | 1. team review 2. uploaded in github in editable format in design folder 3.uploaded in document folder as jpg 4. present to ateam | Done | 2 days
7 | Write overview text, business requirements table, a text describing each persona and journey figure | Ilkay | Task 6 is finished | 1. team review 2. uploaded to github | Done | 1 day
8 | Write text describing each HI-FI mockups screen | Ilkay | Task 4 is finished | 1. team review 2. uploaded to github 3. present to a team | Done | 2 days
8b | Create user stories and add it to doc | Ilkay | Task 4 is finished | 1. team review 2. uploaded to github 3. present to a team | In process
9 | Write solution chapter (architecture, roles) chapter | Marcus | No | 1. team review 2. all figures are uploaded in github in editable format in design folder 3. all figures are uploaded in document folder as jpg 4. present to a team | In process
10 | Add 5-10 sientific references to the document | Marcus | No | 1. team review 2. uploaded to github 3. present to a team | In process
11 | Combine all chapters in one document and finalise document (glossary, references, figures, tables) | Marcus | Tasks 4,6-10 are finised | 1. team review 2. uploaded to github 3. present to a team | New
11b | Create UML diagram explayning our database and write a text | Marcus | Task 2 is finished | 1. team review 2. uploaded to github 3. present to a team | New
12 | Filled historicaldata (solutions and tickets) in SupportTicketingSystem/BackendSystem/HISTORYDATA.xlsx | Marcia | Task 5 is finished | 1. team review 2. uploaded to github 3. present to a team | In process
13 | Check ODATA API with POSTMAN. Do we have all ODATA functionality regarding our mockup? | Shamil | Tasks 1-11b are finished | 1. team review | New
14 | Check ODATA API with POSTMAN. Do we have all ODATA functionality regarding our mockup? | Ilkay | Tasks 1-11b are finished | 1. team review | New
15 | Check ODATA API with POSTMAN. Do we have all ODATA functionality regarding our mockup? | Marcus | Tasks 1-11b are finished | 1. team review | New
16 | Check ODATA API with POSTMAN. Do we have all ODATA functionality regarding our mockup? | Marcia | Tasks 1-12 are finished | 1. team review | New
17 | ODATA. Add navigation between solution category and solutions | Shamil | Task 2 is finished | test | Done | 0,5 day
18 | ODATA. Implement substringof funtion for solution description field | Shamil | Task 2 is finished | test | Done | 0,5 day
19 | Generate test data. Upload data from Historical data xls | Shamil | Task 12 is finished | test | In process | 1 hour
20 | Generate UI (analytics, solutions, solcategoties, tickets) | Shamil | Task 17 is finished | test | Done | 1 hour
21 | Start developing Analytics app UI part | Shamil | Task 13 is finished |  | New
22 | Start developing Solution Categories app UI part | Marcia | Task 16 is finished |  | New
23 | Start developing solutions app UI part | Ilkay | Task 14 is finished |  | New
24 | Start developing tickets app UI part | Marcus | Task 15 is finished |  | New